## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Initialization & Requirement Analysis | MUST HAVE | No Dependency | Hariprasath B | 3- Completed
S1 | S1 | US-002 | System Architecture Design (Backend + ML + DB) | MUST HAVE | Draw.io | Hariprasath B | 3- Completed
S2 | S2 | US-003 | Database Design (MySQL Tables & Schema) | MUST HAVE | MySQL Workbench | Hariprasath B | 3- Completed
S2 | S2 | US-004 | Transaction Simulation Engine Development | MUST HAVE | Java, Spring Boot | Hariprasath B | 3- Completed
S3 | S3 | US-005 | Fraud Detection Logic (Rule-Based + ML Integration) | MUST HAVE | Python ML Model | Hariprasath B | 3- Completed
S3 | S3 | US-006 | REST API Development | MUST HAVE | Spring Boot | Hariprasath B | 3- Completed
S4 | S4 | US-007 | Frontend Development (React Dashboard UI) | MUST HAVE | React.js | Hariprasath B | 3- Completed
S4 | S4 | US-008 | Analytics Dashboard | SHOULD HAVE | Chart.js | Hariprasath B | 3- Completed
S5 | S5 | US-009 | JWT Authentication & Admin Security | MUST HAVE | Spring Security | Hariprasath B | 3- Completed
S5 | S5 | US-010 | System Integration | MUST HAVE | API Integration | Hariprasath B | 2- In Progress
S6 | S6 | US-011 | Testing (Unit + System) | MUST HAVE | JUnit, Postman | Hariprasath B | 2- In Progress
S6 | S6 | US-012 | Deployment | MUST HAVE | Render / Vercel | Hariprasath B | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 8 | 23 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Requirement Analysis & Planning | 04-Feb-2026 | 06-Feb-2026 | Hariprasath B | Planning | 3- Completed | 8
[8 empty] | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | Transaction Generator Development | 13-Feb-2026 | 16-Feb-2026 | Hariprasath B Vetrivel R | Coding | 3- Completed | 12 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Fraud Rules Implementation | 17-Feb-2026 | 20-Feb-2026 | Hariprasath B Vetrivel R | Coding | 3- Completed | 12 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 6 | ML Model Integration | 21-Feb-2026 | 24-Feb-2026 | Hariprasath B | ML | 3- Completed | 12 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 7 | REST API Development | 25-Feb-2026 | 27-Feb-2026 | Hariprasath B | Backend | 3- Completed | 10 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 8 | Frontend Development | 28-Feb-2026 | 04-Mar-2026 | Hariprasath B | Frontend | 3- Completed | 12 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 9 | Analytics Dashboard | 05-Mar-2026 | 08-Mar-2026 | Hariprasath B | Frontend | 3- Completed | 10 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 10 | JWT Security | 09-Mar-2026 | 12-Mar-2026 | Hariprasath B | Security | 3- Completed | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 11 | Integration | 13-Mar-2026 | 18-Mar-2026 | Hariprasath B | Integration | 2- In Progress | 12 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 12 | Testing | 19-Mar-2026 | 25-Mar-2026 | Hariprasath B | Testing | 2- In Progress | 10 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 13 | Deployment | 26-Mar-2026 | 31-Mar-2026 | Hariprasath B | Deployment | 2- In Progress | 8 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on D5: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E5: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unclear system architecture | Researched and finalized architecture
Sprint 2 | Day 5 | Database schema difficulty | Used ER diagrams
Sprint 3 | Day 14 | ML integration issue | Used API approach
Sprint 4 | Day 28 | Frontend API errors | Debugged using Postman
Sprint 5 | Day 35 | JWT issues | Fixed token validation
Sprint 6 | Day 43 | Deployment errors | Fixed environment configs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 04/02/2026 | 09/02/2026 | Hariprasath B | Plan before coding | Avoid assumptions | Follow structure | Improved clarity
2 | Sprint 2 | 10/02/2026 | 16/02/2026 | Hariprasath B , Vetrivel R | Better DB design | Ignore edge cases | Optimize queries | Efficient schema
3 | Sprint 3 | 17/02/2026 | 24/02/2026 | Hariprasath B | Test ML output | Blind coding | Debug step-by-step | Accuracy improved
4 | Sprint 4 | 25/02/2026 | 08/03/2026 | Hariprasath B | Clean UI | Rushing UI | Improve UX | Better dashboard
5 | Sprint 5 | 25/02/2027 | 08/03/2027 | Hariprasath B | Clean UI | Rushing UI | Improve UX | Better dashboard
6 | Sprint 6 | 19/03/2026 | 31/03/2026 | Hariprasath B | Test before deploy | Skip testing | Ensure stability | Smooth deploy
7